# eConX Loan Module - Client Scope, Delivery Plan, and Effort Estimate (Phases 1 and 2)

Prepared for client review and commercial sign-off

# 1. Executive summary

This document describes the Phase 1 and Phase 2 scope, delivery plan, resourcing and effort estimate for the eConX Loan Module. The scope is based on the co-development meeting videos and requirements. Phase 1 covers the lending workflow up to offer/legal docs and acceptance/loan setup. Phase 2 adds repayments and Direct Debit collections (file-based).

## 1.1 Key outcomes by end of Phase 1

Stage model in eConX: enquiry, application, assessment, approval, offer/legal docs, acceptance/loan setup (servicing excluded in Phase 1).

ENI admin console: dashboard queues, case tracking across all stages, tasks and follow-ups, and a unified document library per case.

Digital forms: NISBLF Application Form (primary contact) and Supplementary Application Form (per beneficial owner) completed and signed within eConX.

Manual checks (Phase 1): upload proof of identity/address and Equifax credit evidence, and record outcomes to gate progression.

UCF approver access: restricted approval view with approve, query-back, and decline decisions plus auditable comments.

Offer management: CCA and Non-CCA packs, APR field, repayment day (Day 1 or Day 17), guarantee requirements, and template-driven document generation.

Digital delivery and signing: legal documents pre-populated from eConX data and completed/signed within or through eConX (e-sign provider to be DocuSign or alternate).

Acceptance workflow: capture acceptance outcome, agreement date, bank details, and create a Loan record (Phase 1 lite).

Operational reporting: pipeline by stage, time period, approvals/declines, and audit exports (CSV).

Implementation readiness: configuration, permissions, and audit logging suitable for production go-live at the end of Phase 1.

## 1.2 Delivery approach

Phase 1 will deliver the end-to-end lending workflow (through offer/legal docs and acceptance/loan setup) in six 2-week sprints plus a short launch window. Phase 2 (repayments and Direct Debit collections) is planned immediately after Phase 1 go-live and is sized as an additional four 2-week sprints, subject to bank file format confirmation.

# 2. Context and assumptions

The following are treated as confirmed MVP requirements and assumptions for delivery:

Loan operations are ENI-only in Phase 1 (no LEA loan processing).

Front-door website remains separate from eConX due to NISBLF brand; Phase 1 supports enquiry/application handoff into eConX (import/API mechanism to be confirmed).

Phase 1 covers lending workflow up to acceptance and loan setup; repayments/collections and bank file exchange are Phase 2.

Credit checks (Equifax) and AML/ID/address verification are manual in Phase 1 with evidence upload and outcome capture (no bureau API integration).

Approval includes a restricted UCF approver view (approve, query-back, decline) with auditable comments.

Offer types include CCA and Non-CCA; templates will be generated and pre-populated from eConX data (exact layout parity not required).

Digital signing is required for Application/Supplementary forms and legal packs; e-sign provider to be confirmed (DocuSign acceptable).

Repayment day must support Day 1 vs Day 17 (legacy parity); first repayment date rules are implemented in Phase 2.

Bank is assumed to be Bank of Ireland for planning purposes; file formats for Direct Debit submissions/returns to be confirmed during Phase 2 discovery.

Customer authentication is email/password; beneficial owners may be invited via secure link if not existing users.

Data migration approach: import in-flight cases and active loans into eConX; historic/closed cases are optional and can be handled as read-only archive if required.

# 3. MVP scope overview

## 3.1 Modules in scope (Phase 1)

| Module | What it includes (MVP) |
| --- | --- |
| Operational dashboard & queues | Work queues and alerts to mirror legacy operational workflow. |
| Enquiry, application, assessment tracking | Case lifecycle tracking with stage/outcome fields and history. |
| Duplicate resolution (enquiry) | Flag potential duplicate organisations and link to existing record. |
| Tasks & follow-up | To-do list and follow-up dates per case. |
| Assessment pack | AML checklist, credit check evidence, commitments table (line-item list of recurring monthly financial commitments with auto-calculated totals for affordability), assessment memo upload. |
| Approvals | Internal approval capture plus restricted UCF approver portal workflow (approve / query-back / decline) with auditable comments. |
| Offer management | CCA/Non-CCA, APR, repayment day, subordination required, offer statuses. |
| Doc generation & DocuSign | Generate PDFs and send DocuSign for email-based signing. |
| Conditions & requirements | Checklist gating progression to approval and offer issuance (e.g., ID/address evidence attached, credit evidence attached, application signed). |
| Disbursement | Queue of loans ready to disburse and auditable disbursement recording. |
| Loan setup (Phase 1 lite) | Create Loan record upon acceptance, store bank details and mandate status, and snapshot key offer terms for later servicing. |
| Repayments & collections (Phase 2) | Repayment schedule, Day 1/Day 17 collection cycles, Direct Debit batch files, return file ingestion, reconciliation, arrears and statements (delivered in Phase 2). |
| Customer portal | Customer portal for application completion, supplementary participant invites, document upload, status tracker and e-signing. |
| Notifications + communications log | Email/SMS notifications plus communications audit trail. |
| Reporting exports | Pipeline and conversion reports, on-demand CSV/PDF. |

## 3.2 Phase 2

Repayment schedule calculation, collections batching, Direct Debit submission files, return file ingestion, arrears management and statements.

Automated credit bureau API integration (Equifax/other) and automated AML provider integration (Phase 2+ if required).

Complex multi-party signing beyond agreed flows (e.g., multi-envelope signing with conditional routing) (Phase 2+ if required).

Advanced reporting parity with legacy (full filter sets and bespoke MI pack) (Phase 2+).

# 4. Detailed functional requirements

## 4.1 Operational dashboard (queues and alerts)

Enquiries requiring verification.

Incomplete enquiries / applications / assessments.

Supplementary forms outstanding (per beneficial owner).

Approvals pending (UCF decision required).

Offers/legal packs awaiting generation, sending, or signature.

Cases awaiting manual checks completion (ID/address/credit evidence).

Accepted offers pending loan setup (bank details capture and loan record creation).

Overdue follow-ups and ageing alerts (by stage).

## 4.2 Enquiry intake and duplicate resolution

Import-first in MVP; web intake can be enabled later without schema changes.

Capture referral source, loan amount sought, free-text details, follow-up date, and outcome (reject / proceed / refer).

Duplicate detection: show possible existing organisations; user selects existing or confirms new.

## 4.3 Case tracking (enquiry - application - assessment - approval - offer)

Stage and outcome fields per case (including legacy-style outcomes such as proceed to assessment, proceed to approval, accepted).

Docs send to: store a recipient selector (organisation vs main contact) to drive outbound communications.

Full audit history of stage changes and edits.

## 4.4 Tasks and follow-up

To-do list per case with due dates and completion tracking.

Follow-up date as a first-class field used in queues and reminders.

## 4.5 Assessment pack (AML, credit, commitments)

AML checklist (manual) with reviewer, timestamps and notes.

Credit check method field (Equifax/manual) and uploaded evidence report.

Commitments table (replacement for the current spreadsheet summary): a structured, line-item table of each applicant’s and beneficial owner’s recurring financial commitments (e.g., loans, credit cards, HP/finance, mortgage/rent where applicable), capturing the monthly (or monthly-equivalent) payment amount per line and auto-calculating totals used for affordability review.

Ability to attach or generate an assessment memo document (upload in MVP; system-native form can be Phase 2).

## 4.6 Approvals

Internal approval capture (approve/reject + reasons).

Third-party (UCF) approvals completed via a restricted approver portal workflow in Phase 1 (approve / query-back / decline) with mandatory reasons/comments and a full audit trail. Approval documents (if any) can also be uploaded and linked to the decision record.

## 4.7 Offer management + DocuSign

Offer types: CCA and Non-CCA (seeded from legacy list).

Fields: APR (supports 0%), repayment day (Day 1 or Day 17), loan subordination required flag, term, principal.

PDF generation from templates (non-strict formatting in MVP).

DocuSign email-based signing; store envelope status and signed PDFs.

## 4.8 Conditions/requirements and disbursement

Conditions checklist (template per offer type) that can include: AML complete, credit evidence attached, mandate ready, guarantee uploaded, subordination docs, additional data requested.

Disbursement queue: only cases with all required conditions satisfied can be marked ready to pay out.

Disbursement recording: date, amount, reference, user, and audit trail.

## 4.9 Repayments and Direct Debit collections (Phase 2)

Repayment schedule calculation from accepted offer terms (amount, term, APR/flat type) with working-day rules for Day 1/Day 17 cycles.

Collections batching twice monthly (Day 1 and Day 17) with auditable batch states: draft, generated, uploaded, settled, returned, closed.

Outbound Direct Debit submission file generation via a pluggable formatter (assume Bank of Ireland channel; actual file format to be confirmed).

Inbound return/unpaid file ingestion (bank-provided XML or other) with matching to batch items, reason code capture, and reconciliation workflow.

Repayment anomalies: manual repayments, part payments, repayment holiday, reschedule, early settlement, reversal/refund (policy to be confirmed).

Arrears tracking to match the existing system: track arrears amount, missed instalments, failed repayment counts/reasons, and simple ageing buckets for operational visibility. Create follow-up tasks for failed/overdue repayments (no additional escalation automation beyond legacy parity).

Loan servicing UI: schedule view, transaction ledger, batch history, mandate status, and audit trail.

Reporting: collections performance (expected vs collected vs failed), arrears, and month-end extracts.

## 4.10 Statements and month-end (Phase 2)

Annual statements generation queue for CCA loans (PDFs stored to document repository).

Month-end checklist indicators and month-end reporting extracts.

## 4.11 Customer portal

Status tracker (customer-friendly stages) and clear outstanding actions (forms to complete, docs to upload, signatures pending).

Digital completion of the Application Form and Supplementary Application Form (per beneficial owner) with e-signature.

Document uploads with required-document prompts and validation (where applicable).

E-sign status visibility (sent, viewed, signed) and access to signed copies.

Secure messaging / query-back responses within the application record, with attachments stored to the case library and full audit history.

## 4.12 Notifications and communications log

Email and SMS notifications for key events (document requested, offer sent, signing complete, payment failed, holiday decision).

Store communications log entries with channel, recipient, template key, delivery status.

# 5. Technical approach (high-level)

Implementation will be a modular addition to the existing eConX platform (Laravel backend + React frontend) reusing existing RBAC, audit trail, document storage, and AWS-based notifications. The loan module will be logically isolated (separate tables, services, UI routes) to support future expansion.

## 5.1 Integrations

DocuSign: send envelopes for signing and receive webhook updates (email-based signing).

Direct Debit collections (Phase 2): generate submission files for bank upload and ingest return/unpaid files for reconciliation (file-based integration; Bank of Ireland assumed for planning).

Credit checks: manual evidence capture in MVP; integration capability can be added later.

## 5.2 Placeholder (unclaimed) accounts for missing email

Imported cases may not have an email address. To avoid blocking import and portal access, the system will support unclaimed placeholder accounts. A placeholder cannot log in until a real email is added. When an email becomes available, ENI can link the case to an existing user or convert the placeholder into an active account and send a set-password email.

# 6. Delivery plan and timeline

Delivery is planned across six 2-week sprints, followed by a short launch window for production readiness and go-live support.

| Sprint | Duration | Key deliverables | Acceptance criteria (summary) |
| --- | --- | --- | --- |
| Sprint 1 | 2 weeks | Foundations: data model, RBAC, audit logging, unified document library skeleton, environment setup | Core entities created; audit trail works; document upload/store works; environments ready |
| Sprint 2 | 2 weeks | Case workflow v1: enquiry -> application -> assessment; dashboard queues; tasks & follow-up; basic reporting | Queues show correct counts; stage transitions audited; tasks due dates drive reminders; CSV export works |
| Sprint 3 | 2 weeks | Digital forms v1: Application Form (primary contact) + Supplementary Form (beneficial owners) + secure invites + e-sign | Primary contact can complete/sign; beneficial owners invited and can complete/sign; form snapshots stored and auditable |
| Sprint 4 | 2 weeks | Assessment v1: manual AML/ID/address/credit check capture + evidence upload; UCF approver restricted view + query loop | Manual checks recorded with outcomes; progression gating works; UCF can approve/query/decline with comments and notifications |
| Sprint 5 | 2 weeks | Offer & legal docs v1: CCA/Non-CCA pack generation, pre-population, digital delivery, signing workflow | Templates generate correctly; merge fields populated; signing status tracked; signed copies stored in library |
| Sprint 6 | 2 weeks | Acceptance + loan setup; bank details capture; loan record creation (Phase 1 lite); hardening, UAT fixes, migration runbook | Accepted cases create loan record; bank details captured; audit complete; UAT sign-off; go-live checklist ready |
| Launch window | up to 1 week | Production readiness + go-live support | Production deploy completed; monitoring enabled; initial import/handoff executed; support coverage in place |

## 6.1 Dependencies

Bank submission/return file specifications or samples (Phase 2) - required to validate formatter/parser (Bank of Ireland assumed).

NISBLF/KCONI export samples - expected within ~10 days.

DocuSign account configuration and webhook access in staging and production.

## 6.1 Phase 2 delivery plan (repayments and Direct Debit collections)

Phase 2 is planned as four additional 2-week sprints immediately after Phase 1 go-live. Exact sequencing can be confirmed once bank file formats and reason-code taxonomy are validated.

| Sprint | Duration | Key deliverables | Acceptance criteria (summary) |
| --- | --- | --- | --- |
| Sprint 7 | 2 weeks | Repayment schedule engine + first repayment date rules (Day 1/Day 17 + working-day calendar) + servicing UI skeleton | Schedule generated from offer terms; first repayment date calculator produces explainable outcomes; loan view shows schedule/ledger |
| Sprint 8 | 2 weeks | Collections batching + outbound submission file generation (pluggable formatter; assume Bank of Ireland) + batch audit trail | Day 1/Day 17 batches created; file generated and versioned; batch states and totals correct; operator workflow complete |
| Sprint 9 | 2 weeks | Return/unpaid file ingestion (bank-provided XML or other) + matching/reconciliation UI + reason code capture + tasks | Return import updates batch items; failures recorded with reasons; unmatched items queued; follow-up tasks created |
| Sprint 10 | 2 weeks | Anomalies (manual/part payments, holidays, reschedules, settlement) + arrears tracking + collections reporting pack | Anomalies applied with audit trail; arrears buckets correct; expected vs collected vs failed reports available; month-end extracts |

# 7. Resourcing and effort estimate

The plan below is sized to meet the  deadline. Hours assume a 37.5 hour working week.

## 7.1 Team plan (deadline-driven)

| Role | FTE | Hours (Phase 1 + Phase 2) | Notes |
| --- | --- | --- | --- |
| Backend Engineer (Laravel) | 3.0 | 1,100 (P1) + 650 (P2) = 1,750 | Core workflow, forms, docs, approvals, offer/legal docs (P1) plus schedule/batching/returns/anomalies (P2). |
| Frontend Engineer (React) | 2.0 | 820 (P1) + 350 (P2) = 1,170 | Admin console + customer portal + approval UX (P1); servicing UI + reconciliation screens (P2). |
| QA Engineer | 1.0 | 480 (P1) + 260 (P2) = 740 | Test plans, automation where feasible, UAT support (both phases). |
| Tech Lead / Architect | 0.5 | 220 (P1) + 120 (P2) = 340 | Design governance, code review, risk management. |
| PM/BA | 0.5 | 240 (P1) + 120 (P2) = 360 | Requirements, client demos, acceptance criteria, UAT coordination. |
| DevOps/Platform | 0.5 | 180 (P1) + 80 (P2) = 260 | Deployments, secrets, monitoring, staging/prod readiness. |

Total planned delivery hours: approximately 4,620 hours (including QA/PM/Tech Lead/DevOps). This is a deadline-driven plan; if resourcing is reduced, scope or delivery date must change.

## 7.2 Effort breakdown by workstream (engineering)

| Workstream | Estimated hours |
| --- | --- |
| Foundations + RBAC + audit + admin console + dashboard queues (Phase 1) | 320 |
| Enquiry/application workflow + tasks/follow-up + duplicate resolution + handoff/import (Phase 1) | 360 |
| Digital forms: Application + Supplementary (per beneficial owner) + e-sign capture (Phase 1) | 320 |
| Assessment pack: manual AML/ID/address/credit checks + evidence upload + gating (Phase 1) | 260 |
| UCF approval workflow: restricted view + approve/query/decline + notifications (Phase 1) | 220 |
| Offer management + legal pack generation (CCA/Non-CCA) + pre-population + delivery + signing (Phase 1) | 420 |
| Customer portal UX: status tracker, uploads, invites, signatures (Phase 1) | 240 |
| Loan setup (Phase 1 lite): acceptance outcomes + agreement date + bank details + loan record creation | 140 |
| Repayments & collections batching + outbound submission file generation (Phase 2) | 420 |
| Return/unpaid import + reconciliation + arrears + statements/month-end extracts (Phase 2) | 420 |
| Notifications + communications log (Phase 1) | 160 |
| Reporting exports and MI basics (Phase 1 + Phase 2) | 200 |
| QA + UAT (test planning, regression, release validation) (Phase 1 + Phase 2) | 480 |

Total estimated hours (engineering + QA): approximately 3,180 hours.

## 7.3 Commercial estimate (pricing)

Pricing can be derived by applying an agreed blended hourly rate to the planned delivery hours.
Estimated cost = Total hours x Blended hourly rate

Total hours (delivery plan): 4,620
Recommended contingency: 10-15% until bank formats and legacy exports are validated.

# 8. Risks, assumptions and mitigations

| Risk / dependency | Impact | Mitigation |
| --- | --- | --- |
| Bank Direct Debit submission/return formats differ from assumptions (Bank of Ireland assumed) | High | Implement formatter/parser abstraction; confirm bank/portal and obtain sample files early in Phase 2; include manual mapping UI for unmatched returns. |
| Handoff/import mapping from legacy is incomplete or changes during delivery | High | Validate mapping in Sprint 1-2 with client sample exports; design for iterative mapping; log and report unmapped fields. |
| E-sign provider/legal acceptance is not confirmed early | Medium | Proceed with DocuSign-compatible design; keep provider-agnostic integration layer; confirm before Sprint 5 to avoid rework. |
| UAT feedback arrives late in Phase 1 | High | Weekly demos; freeze scope end of Sprint 5; reserve Sprint 6 for UAT fixes/hardening; define acceptance criteria per sprint. |
| Repayment policy edge cases (holidays, settlements, part-payments) are not fully defined | Medium | Define a small set of supported anomaly policies for Phase 2; implement with audit trail; allow manual override; expand in Phase 2.1 if needed. |
| Legal document templates and merge-field dictionary require cleanup/standardisation | Medium | Agree template sources and merge-field list early; generate and review sample packs in Sprint 5; treat formatting parity as non-blocking unless legally required. |

# Appendix A: Legacy parity checklist (high-level)

Dashboard queues (Phase 1): verification, incomplete records, supplementary outstanding, approvals pending, offers pending signature, loan setup pending.

Enquiries: referral source, follow-up date, accept/reject/proceed/refer outcomes, duplicate resolution.

Applications: docs-send-to (organisation vs main contact).

Assessments: Equifax/manual evidence, commitments table, to-do list integration.

Offers: CCA/Non-CCA, APR, repayment day Day 1/17, subordination required, accepted/signed status.

Conditions checklist gating progression to approval and offer issuance (Phase 1) and, later, disbursement/servicing readiness (Phase 2).

Disbursement queue and audit record.

Servicing (Phase 2): schedule, batching, submission file generation, upload tracking, returns ingestion/reconciliation, re-collect logic, failure reasons.

Statements and month-end (Phase 2): annual statements (CCA) queue and month-end indicators/extracts.

Repayment anomalies (Phase 2): payment holidays, manual/part payments, reschedules and settlements (policy-defined).